## Sheet1
Risk Register
Risk Categories | Numbers of risks | Risk SubTitles | Risk Probability | Risk Impact
Resources | 1 | Human Resources not available at time | 6 | 7
| 2 | Facilities are not provided | 7 | 8
| 3 | Equipments are not available at time | 5 | 8
| 4 | If the quality of the resources is low | 5 | 9
Financial | 5 | Over Budget of the cost for the project | 8 | 9
| 6 | Lack of proper Cash Flow | 6 | 10
| 7 | Late Payments from the client | 4 | 8
| 10 | Changing currency to lower rate currency | 3 | 7
| 11 | If somehow couldn't get enough benefit from the project | 4 | 9
| 12 | If Accountant is messing up with the accounts | 2 | 8
Client | 13 | Unavailability of the client | 3 | 8
| 14 | Uncooperative while having discussions or sprints | 2 | 6
| 15 | Unexpected change in demands of the project | 4 | 7
| 16 | Client access distrupted(eg road construction infront of office) | 1 | 7
| 17 | If Reputation of client is not good | 2 | 7
Hosting | 18 | Problems with the hosting online | 3 | 7
| 19 | Server Issues, not connecting or server down | 4 | 7
| 20 | Data Loss because of any reason | 2 | 8
| 21 | The server capacity initially defined may be inadequate | 5 | 5
Sope Change | 22 | Scope Creep | 4 | 9
| 23 | Going out of scope | 6 | 8
Schedule | 24 | Unrealistic Schedule of the employee | 7 | 7
| 25 | Not meet the deadline of the project | 5 | 9
Buisness | 26 | Non availability or issues with the contract | 3 | 7
Technology | 27 | Tech Resources problems (Wifi, equipments) | 4 | 7
| 28 | High level of technical complexity | 2 | 8
Legal Risk | 29 | Legal risk from the client or external risks | 2 | 6
| 30 | Buisness license not reneued at time | 6 | 6
| 31 | If the project undertaken from the client is not legal | 4 | 7
| 32 | Insurance for the company not paid at time | 5 | 5
Design Surveys | 33 | Stake holders not showing up their interest | 4 | 6
| 34 | Connection problems while doing online surveys | 5 | 6
Website Design | 35 | Third part frameworks not available | 3 | 6
CMS Setup | 36 | Issues or Bugs configuring CMS | 4 | 7
| 37 | RSS feeds not available | 3 | 4
Integrate google calender | 38 | Issues connectiong with google services | 5 | 3
Online payments | 40 | Network connection problem with online payment services | 6 | 6
Social Media | 41 | Problems integrating social media services | 7 | 4
SEO | 42 | Issues with SEO integration | 5 | 5
| 43 | SEO plugins not available | 4 | 3
Human Resources | 44 | Poor Environment impacts the health of employee | 6 | 7
| 45 | Developers outright leave in the middle of a project | 3 | 9
| 46 | Users not committed to the project | 4 | 4
| 47 | Inexperience team members | 3 | 8
| 48 | Inadequately trained development team members | 4 | 8
| 49 | Users with negative attitudes toward the project | 5 | 6
| 50 | Lack of cooperation from users | 4 | 6
Content Population & Functionality | 51 | Issues migrating data to new website | 3 | 6
| 52 | Amount of data is too much, more then excepted | 4 | 2
| 53 | Expired content notifier stops working | 3 | 4
| 54 | No explicit define about the standard of project qualities | 4 | 5
| 55 | Lack of understand the structuring of content | 3 | 3
| 56 | Authentication failure for content editing | 2 | 4
Additional Functionality | 57 | Spell checker for content editing stops working | 3 | 2
| 58 | No one available for emergency live support | 6 | 3
| 59 | Functionality for automatic sitemap not working | 3 | 3
| 60 | Configuration of third party plugins | 2 | 2
| 61 | Problems integrating google analytics | 4 | 2
Technical | 62 | Complexity of designing models increases by using mobile devices | 3 | 2
| 63 | Menu items not get update automatically | 2 | 3
| 64 | Laptop or computer been corrupted by the virus | 3 | 6
Employees Related Risk | 65 | Employees don't enter their time in timesheet | 7 | 9
| 66 | If Employee doesn't show the reciept of food and travel expenses | 6 | 7
| 67 | If Employee Steel data or ideas and sell them to other company | 5 | 8
| 68 | Lack of traning for the entire project to be done | 3 | 8
| 69 | If lot of controversy among team members | 5 | 6
| 70 | Poor communication skills to communicate with team members and client | 4 | 9
| 71 | Employees handing out thier work late | 3 | 7
| 72 | Bad reputation of employee | 2 | 7
Quality Risk | 73 | Poor planning for the start up of the project | 1 | 8
| 74 | High rework expense, if client doesn't like the thing | 6 | 7
| 75 | Poor employee moral to do their stuff | 3 | 5
Others | 76 | Page loading time might depend upon internet | 2 | 4
| 77 | Too many people involved in the decision process | 5 | 6
| 78 | The back-end functionality coding is inefficient | 3 | 6
| 79 | Site is not accessible for launch date | 4 | 8
| 80 | If Planning for the project is not good | 3 | 7
| 81 | Physical Destruction at place of work | 2 | 5
| 82 | Not addressing in the planning phase how much input is required by the client during the project | 4 | 5
| 83 | Requirements and developed functions do not match | 3 | 6
| 84 | User interfaces do not fit needs | 4 | 6
| 85 | Inadequate architecture, performance, quality | 3 | 6
| 86 | Constant alteration of requirements | 2 | 7
| 87 | Problems with tasks performed externally | 6 | 6
| 88 | Price increases in critical inputs | 3 | 7
| 89 | Risk of damaging relationship with the client | 4 | 8
| 90 | Choosing a bad location to work in | 3 | 5
| 91 | Infrastructure risk, example electricity outage | 4 | 8
| 92 | Lack of effective project management methodology | 2 | 7
| 93 | Failure to manage end-user expectations | 1 | 6
| 94 | Developing the wrong user interface | 2 | 7
| 95 | Inadequate security features being built into the website | 4 | 6
| 96 | Failure of not getting all the work done as described in RFP | 7 | 8
| 97 | Project progress not monitored closely enough | 6 | 8
| 98 | Project Milestones not clearly defined | 6 | 7
| 99 | Not enough or no security outside the office | 2 | 5
| 100 | If employees increase their demands or pay | 3 | 6